## Sheet1
Test Case created : Gangadhara Matti Test Case reviewed : Aneesh Dalvi Test Case created : 10/14/2018 Test Case review : 10/14/2018 Linked User Story : 8 and 12
Sr. No. | Task | Expected Result | Tester 1 | Result | Description | Tester 2 | Result
1 | Go to the task URL, in our case currently it's 'http://localhost:5000/' | The website homepage should launch, without being logged in and the UI should display the posts from the database - Unregistered user should be able to see the posts. | Gangadhara Matti | Pass |  | Pass
2 | Scroll to the end of the page - "Web Forum" | The "Create Post" button should not be visible. | Gangadhara Matti | Pass |  | Pass
3 | Add some dummy data into the posts table | The data should be visible in the table correctly | Gangadhara Matti | Pass |  | Pass
4 | 1. Click on Register 2. Enter Name: "SP2US8Test" 3. Enter Email : "sp2us8test@gmail.com" 4. Enter Password : "asu" 5. Confirm Password: "asu" 6. Click on submit button | A message "You have registered successful" should be displayed and login screen should be visible | Gangadhara Matti | Pass |  | Pass
5 | Login with the Email and password given above | The UI should show you home page with all the posts displayed one by one in timestamp and create post button at the end of the page. Compare the posts values from the database and they should be same. | Gangadhara Matti | Fail | Posts are not ordered according to timestamp Bug raised in Taiga https://tree.taiga.io/project/meng-ze-breitenburg-ser515/issue/65 | Fail
6 | Search for a title of the post which(for example: "XXXXX") is not in the database and click search. | The UI should show "No results found!" and no posts should be displayed | Gangadhara Matti | Pass |  | Pass
7 | Search for a post title which is in the database | The UI should show that particular post and no other posts and it should display a message "Values Found!" | Gangadhara Matti | Pass |  | Pass